## Time Schedulde Bachelot Thesis
Time Schedule Bachelor Thesis |  | Hardtung SoSe20
|  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | (Month 4)
| Week | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Planning |  | 0: Orientation
First Research and Ressource Sighting | bar: 0
Define Problem and Goal | bar: 0
Plan Bachelor Thesis Structure Tentatively | bar: 0
Write Exposé | bar: 0
Research & Material |  | 1: Research & Material
Intensive Search for Literature and Analysis | bar: 1 to Month 1 2
Choose Specific Evaluation Methods | bar: 1 to Month 1 2
Carry out Evaluation | bar: Month 1 3 to Month 1 5
Dataanalysis | bar: Month 1 4 to Month 1 5
Writing |  | 1: Writing
Collect Sources | bar: 0 to Month 2 6
Abstract | bar: Month 1 2
Introduction | bar: Month 1 2
Justify Use of Chosen Evaluation Methods | bar: Month 1 2 to Month 1 3
| Evaluation of the Origrammer | (Month 4) 14: (If needed)
Sort Found Flaws by Severity | bar: Month 1 5
Plan Features that Fix Mentioned Flaws | bar: Month 1 5 to Month 2 6
Weigh Solutions up Against Each Other | bar: Month 2 6 to Month 2 7
Evaluate Implemented Solutions | bar: Month 2 7 to Month 2 9
Problems & other Findings | bar: Month 2 9 to Month 3 10
Prospect | bar: Month 2 9 to Month 3 10
Programming |  | Month 1 5: Programming & Implementation
Implement the Planned Features | bar: Month 1 5 to Month 3 10
Comment Code | bar: Month 1 5 to Month 3 10
Code Optimizations | bar: Month 2 8 to Month 3 10
Cleanup Code | bar: Month 2 9 to Month 3 11
Finishing Stage |  | Month 3 11: Completion
Proofreading (self) | bar: Month 3 11
Proofreading (from outside) | bar: Month 3 11
Plagiarism Assessment | bar: Month 3 11
Check & Finalise Layout | bar: Month 3 12